CREWCIAL PARTNERS ¦ 2026 Sales Activation Phase 3 Launch Gate Checklist Go / No-Go Criteria ¦ April 1, 2026 Launch All items must be confirmed before any consultant begins outreach

| Gate Owner Business Development | Sign-Off Required Dine Grullon (CEO) | Target Launch April 1, 2026 | Status PENDING |
| --- | --- | --- | --- |

The Gate Standard Phase 3 does not launch until every item on this checklist is confirmed. Partial readiness = delayed launch. A consultant who starts outreach without HubSpot setup, without contact assignment, or without signing the policy is a liability — not an asset. BizDev presents this completed checklist to Dine for final go/no-go confirmation at least 3 days before the target launch date.

## Part 1 — Infrastructure (BizDev Completes)

| ☐ | HubSpot license active for all participating consultants | Confirm in HubSpot admin: Settings → Users & Teams |
| --- | --- | --- |

| ☐ | All 6 E&F email templates built in HubSpot library ('Crewcial BD 2026' folder) | Templates → verify 4 themes, 7 templates present |
| --- | --- | --- |

| ☐ | 'Crewcial BD 2026 — Cold Outreach' sequence built and tested | Sequences → verify 4 tasks, auto-unenroll on reply enabled |
| --- | --- | --- |

| ☐ | E&F Question Bank playbook live and accessible from contact records | Playbooks → verify 15 questions across 5 themes |
| --- | --- | --- |

| ☐ | PWI Question Bank playbook live and accessible from COI/PWI contact records | Playbooks → verify 12 questions across 4 themes |
| --- | --- | --- |

| ☐ | COI outreach templates built in HubSpot library ('COI Outreach 2026' folder) | Templates → verify 4 COI types |
| --- | --- | --- |

| ☐ | Podcast outreach templates built in HubSpot library ('Podcast Outreach 2026' folder) | Templates → verify 3 templates |
| --- | --- | --- |

| ☐ | All contacts segmented and Sales Owner field populated for all participating consultants | Contacts → filter by Sales Owner → confirm all names assigned |
| --- | --- | --- |

| ☐ | Lead Warmth, Outreach Status, and Contact Type custom properties visible in all contact records | Contacts → any record → verify custom fields appear |
| --- | --- | --- |

| ☐ | BizDev Ops Dashboard and Leadership KPI Dashboard built and tested | Reports → Dashboards → verify both dashboards populated with live data |
| --- | --- | --- |

| ☐ | BizDev resource page live with links to all supporting documents | All documents uploaded, all links working |
| --- | --- | --- |

## Part 2 — Governance (Leadership Completes)

| ☐ | Phase 1 Sign-Off Document executed with all required signatures (Dine, HR, Mike, consultant rep) | Physical or digital signatures received. Document filed. |
| --- | --- | --- |

| ☐ | CRM Governance Policy co-signed by all participating consultants | All signature lines complete on CRM Governance Policy doc |
| --- | --- | --- |

| ☐ | Year-end bonus weight formally communicated to all consultants | Either via the Sign-Off Document or separate written notice from Dine |
| --- | --- | --- |

| ☐ | Dine confirmed as willing to deliver the Internal Launch Message before Phase 3 start | Launch message reviewed, personalized, and scheduled for delivery |
| --- | --- | --- |

## Part 3 — Consultant Readiness (BizDev Tracks)

| ☐ | All consultants have completed 5 HubSpot fluency proofs (from Setup Guide) | Training Completion Tracker — all 5 proofs logged for all consultants |
| --- | --- | --- |

| ☐ | All Consultant Input Request documents returned to BizDev | One per consultant. Filed. Insights incorporated into contact assignments. |
| --- | --- | --- |

| ☐ | All contact assignments confirmed and communicated to each consultant | Each consultant has received their assigned pool list in writing |
| --- | --- | --- |

| ☐ | Kickoff Meeting Deck reviewed and approved by Dine | Deck confirmed for presentation. All slides accurate. |
| --- | --- | --- |

| ☐ | Phase 2 training session completed and all attendees confirmed ready | Training Completion Tracker — Phase 2 column complete for all consultants |
| --- | --- | --- |

## Part 4 — Content Pipeline (BizDev + Garrett)

| ☐ | At least one piece of outreach-ready content available at launch (article, newsletter, or podcast episode) | Link in BizDev resource page. Ready for consultants to use in Touch 2 or 3. |
| --- | --- | --- |

| ☐ | Shared Content Tracker populated with initial content ideas from Consultant Input Requests | At least 5 ideas in pipeline from pre-kickoff submissions |
| --- | --- | --- |

| ☐ | First roundtable date confirmed on all calendars | Date set, calendar invites sent, advance submission template distributed |
| --- | --- | --- |

## Go / No-Go Sign-Off

| Sign-Off Party | Go / No-Go |
| --- | --- |
| BizDev (Steph) — Infrastructure & Training Gate confirmed Signature & Date | ☐ GO ☐ NO-GO |
| Dine Grullon — CEO authorization to launch Signature & Date | ☐ GO ☐ NO-GO |

A 'No-Go' designation must include a written explanation of what specific item is incomplete and a revised target date. Phase 3 does not begin until a subsequent 'Go' is confirmed in writing.

Crewcial Partners  |  Business Development  |  Confidential